Wastewater Treatment Plants 
ENR Upgrade Status

(June 30, 2007)

Status Update:

Previous Meeting 
 3 facility is in operation 
10 facilities are under construction 13 are under design 
23 in planning 
17 in pre-planning activities

Current 
 5 facilities are in operation 
 9 facilities are under construction.

13 are under design 
22 are in planning 
17 are in pre-planning activities

• The five facilities that are in operation are Celanese, Hurlock, Aberdeen Proving Ground, 	Easton and Swan Point

• Percentage completion for facilities under construction for ENR Upgrade:

Facility 	Percentage complete

Kent Island 
Crisfield 
Chestertown 
Salisbury 
St. Michael’s (Talbot County Region II) Indian Head 
Elkton 
Brunswick 
Havre De Grace

98% 87% 88% 77% 79% 53% 37% 35%  0% (Construction started 6/25/07)

• Construction Permits for ENR Upgrade for both the Georges Creek Wastewater Treatment Plant and Federalsburg Wastewater Treatment Plant have been issued and these facilities are expected to proceed to construction by September 2007. The Georges Creek project is being advertised for bids.

• Events

A dedication ceremony for Easton Wastewater Treatment Plant ENR Upgrade was held on June 13, 2007 at the Easton Wastewater Treatment Plant.